## RICEFW Estimator
Milestones
[21 empty] | 1 | 1a | 2 | 2a | 3 | 3a | 3b | 3c
| RICEFW Estimator | [17 empty] | Dev Type | Complexity | Functional Specification | Functional Specification Review | Technical Specification | Technical Specification Review | Code | Code Unit Test | Code Review | Functnl Test & Business Accptnce | Total Technical Effort (Hours) | Total Functional Effort (Hours) | Total FRICE Effort (Hours)
[19 empty] | Reports - Embedded Analytics | H | 48 | 16 | 24 | 16 | 80 | 32 | 16 | 16 | 184 | 64 | 248
[19 empty] | Reports - Embedded Analytics | M | 32 | 8 | 16 | 8 | 40 | 16 | 8 | 8 | 96 | 40 | 136
[19 empty] | Reports - Embedded Analytics | L | 16 | 4 | 8 | 4 | 24 | 8 | 4 | 4 | 52 | 20 | 72
[19 empty] | Reports - BW/4HANA / BOBJ | H | 48 | 16 | 24 | 16 | 80 | 32 | 16 | 16 | 184 | 64 | 248
[19 empty] | Reports - BW/4HANA / BOBJ | M | 32 | 8 | 16 | 8 | 40 | 16 | 8 | 8 | 96 | 40 | 136
[19 empty] | Reports - BW/4HANA / BOBJ | L | 16 | 4 | 8 | 4 | 24 | 8 | 4 | 4 | 52 | 20 | 72
[19 empty] | Interfaces | H | 56 | 16 | 56 | 16 | 200 | 40 | 20 | 20 | 348 | 76 | 424
|  | Complexity | [16 empty] | Interfaces | M | 40 | 8 | 40 | 8 | 120 | 24 | 12 | 12 | 212 | 52 | 264
| Object Type | Very High | High | Medium | Low | Very Low | Total Type | Very High Factor | 2 |  |  | % Breakdown of FRICE-W Items | [6 empty] | Interfaces | L | 24 | 4 | 24 | 4 | 64 | 16 | 8 | 8 | 120 | 32 | 152
| Reports - Embedded Analytics | 0 | 0 | 0 | 0 | 0 | 0 | Very Low Factor | 0.75 |  |  | Object Type | Very High | High | Medium | Low | Very Low | Type % | Conversions | H | 56 | 16 | 56 | 16 | 160 | 32 | 16 | 16 | 296 | 72 | 368
| Reports - BW/4HANA / BOBJ | 0 | 5 | 10 | 4 | 0 | 19 |  |  |  |  | Reports - Embedded Analytics | 0% | 4% | 14% | 4% | 0% | 22% | Conversions | M | 40 | 8 | 32 | 8 | 96 | 16 | 8 | 8 | 168 | 48 | 216
| Interfaces | 0 | 4 | 10 | 4 | 0 | 18 |  |  |  |  | Reports - BW/4HANA / BOBJ | 0% | 0% | 0% | 0% | 0% | 0% | Conversions | L | 24 | 4 | 16 | 4 | 40 | 8 | 4 | 4 | 76 | 28 | 104
| Conversions | 0 | 0 | 0 | 0 | 0 | 0 | Contingency Factor = | 0% |  |  | Interfaces | 0% | 4% | 10% | 4% | 0% | 18% | Enhancements | H | 48 | 16 | 24 | 16 | 80 | 32 | 16 | 16 | 184 | 64 | 248
| Enhancements | 0 | 4 | 14 | 4 | 0 | 22 | M-hrs Dev with Contingency | 13528 |  |  | Conversions | 0% | 0% | 0% | 0% | 0% | 0% | Enhancements | M | 32 | 8 | 16 | 8 | 40 | 16 | 8 | 8 | 96 | 40 | 136
| Forms | 0 | 4 | 14 | 7 | 0 | 25 | Months of Core Development | 7 |  |  | Enhancements | 0% | 5% | 10% | 4% | 0% | 19% | Enhancements | L | 16 | 4 | 8 | 4 | 24 | 8 | 4 | 4 | 52 | 20 | 72
| Workflow | 0 | 2 | 12 | 2 | 0 | 16 | FTEs / Mo during Core Development Period | 12.0786 |  |  | Forms | 0% | 0% | 0% | 0% | 0% | 0% | Forms | H | 56 | 16 | 28 | 12 | 96 | 16 | 8 | 8 | 176 | 64 | 240
| NWGW | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Workflow | 0% | 4% | 14% | 7% | 0% | 25% | Forms | M | 40 | 8 | 16 | 8 | 56 | 8 | 8 | 8 | 104 | 48 | 152
| UI5 FIORI | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | NWGW | 0% | 2% | 12% | 2% | 0% | 16% | Forms | L | 24 | 4 | 8 | 4 | 24 | 8 | 4 | 4 | 52 | 28 | 80
| Total Complexity | 0 | 19 | 60 | 21 | 0 | 100 |  |  |  |  | UI5 Fiori | 0% | 0% | 0% | 0% | 0% | 0% | Workflows | H | 48 | 16 | 48 | 16 | 160 | 32 | 16 | 16 | 288 | 64 | 352
[8 empty] | Contingency Factor = | 0% |  |  | Complexity % | 0% | 11% | 36% | 13% | 0% |  | Workflows | M | 32 | 8 | 32 | 8 | 80 | 20 | 10 | 10 | 158 | 42 | 200
[8 empty] | M-hrs Functional Support inc Contingency | 4448 | [9 empty] | Workflows | L | 16 | 4 | 16 | 4 | 40 | 12 | 6 | 6 | 82 | 22 | 104
|  | Complexity | [5 empty] | Months of Functional Support | 2 | [9 empty] | NWGW | H | 48 | 16 | 48 | 16 | 160 | 32 | 16 | 16 | 288 | 64 | 352
| Technical Hours | Very High | High | Medium | Low | Very Low | Hour by Type | FTEs / Mo Functional Support | 13.9 | [9 empty] | NWGW | M | 32 | 8 | 32 | 8 | 80 | 20 | 10 | 10 | 158 | 42 | 200
| Reports - Embedded Analytics | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | NWGW | L | 16 | 4 | 16 | 4 | 40 | 12 | 6 | 6 | 82 | 22 | 104
| Reports - BW/4HANA / BOBJ | 0 | 920 | 960 | 208 | 0 | 2088 | [11 empty] | UI5 Fiori | H | 96 | 16 | 96 | 16 | 240 | 48 | 24 | 24 | 440 | 120 | 560
| Interfaces | 0 | 1392 | 2120 | 480 | 0 | 3992 | Tech Stream | Hours | Total Man Month | FTE over Core Dev | [7 empty] | UI5 Fiori | M | 64 | 8 | 64 | 8 | 120 | 32 | 16 | 16 | 248 | 80 | 328
| Conversions | 0 | 0 | 0 | 0 | 0 | 0 | Conversion | 0 | 0 | 0 | [7 empty] | UI5 Fiori | L | 32 | 4 | 32 | 4 | 56 | 16 | 8 | 8 | 120 | 40 | 160
| Enhancements | 0 | 736 | 1344 | 208 | 0 | 2288 | ABAP / SCP | 7448 | 46.55 | 6.65
| Forms | 0 | 704 | 1456 | 364 | 0 | 2524 | Fiori/NWGW | 0 | 0 | 0
| Workflow | 0 | 576 | 1896 | 164 | 0 | 2636 | Integration | 3992 | 24.95 | 3.5643
| NWGW | 0 | 0 | 0 | 0 | 0 | 0 | BW/4HANA / BOBJ | 2088 | 13.05 | 1.8643
| UI5 FIORI | 0 | 0 | 0 | 0 | 0 | 0 | Embedded Analytics | 0 | 0 | 0
| Hours by Complexity | 0 | 4328 | 7776 | 1424 | 0 | 13528
Complexity
| Functional Hours | Very High | High | Medium | Low | Very Low | Hour by Type
| Reports - Embedded Analytics | 0 | 0 | 0 | 0 | 0 | 0
| Reports - BW/4HANA / BOBJ | 0 | 320 | 400 | 80 | 0 | 800
| Interfaces | 0 | 304 | 520 | 128 | 0 | 952
| Conversions | 0 | 0 | 0 | 0 | 0 | 0
| Enhancements | 0 | 256 | 560 | 80 | 0 | 896
| Forms | 0 | 256 | 672 | 196 | 0 | 1124
| Workflow | 0 | 128 | 504 | 44 | 0 | 676
| NWGW | 0 | 0 | 0 | 0 | 0 | 0
| UI5 FIORI | 0 | 0 | 0 | 0 | 0 | 0
| Hours by Complexity | 0 | 1264 | 2656 | 528 | 0 | 4448
Complexity
Object/s Names | Type Of Object | V. High | High | Med | Low | V. Low | Comments
e.g. | Reports - Embedded Analytics
e.g. | Reports - BW/4HANA / BOBJ |  | 5 | 10 | 4 |  |  | Standard RDM objects - Data
e.g. | Interfaces |  | 4 | 10 | 4 |  |  | Transactional Data |  |  | Master Data
e.g. | Conversions |  | 0 | 0 | 0 |  |  | Inventory Balances |  |  | Secondary Cost Element | Inspection Plan
e.g. | Enhancements |  | 4 | 14 | 4 |  |  | Source List |  |  | Characteristic | Bill of Materials
e.g. | Forms |  | 4 | 14 | 7 |  |  | Work Breakdown Structure |  |  | Class | Equipments
e.g. | Workflow |  | 2 | 12 | 2 |  |  | Fixed Assets |  |  | Activity Type | Service Master
e.g. | NWGW | [6 empty] | Purchase Info Record |  |  | Activity Price | Object Dependency
e.g. | UI5 FIORI | [6 empty] | Planned Independent Requirements |  |  | Cost Centers | Material Customer Replenishment
[8 empty] | Order Reservations |  |  | Profit Centers | Reference Operation Sets
[8 empty] | Purchasing Requisition |  |  | Bank Master | Routing
[8 empty] | Contracts |  |  | Exchange Rate | SD Pricing
[8 empty] | Scheduling Agreements |  |  | Work Center | Functional Location
[8 empty] | Sales Order |  |  | Material Master | Cost Center Groups
[8 empty] | Purchase Order |  |  | Material Master Classification | Activity Type Groups
[8 empty] | Internal Order |  |  | Configuration Profile for Material | Profit Center Groups
[8 empty] | Open Deliveries |  |  | Inspection Method | Business Partner (CVI, Cust & Vend)
[8 empty] | Supplier Invoice |  |  | Material Inspection Type | Statistical Key figures
[8 empty] | Credit Memo |  |  | Material Inspection Characteristics | Batch
Customer Invoice Billing

## Resource Loading
Tower 1 | Tower 2 | Tower 3 | Customer Role‑Name | Type of FTE | Destination Location | HCL Role | Level (DONOT HARDCODE) | Total (Mo FTE) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20
| Phase‑1 | ABAP | SAP ABAP Lead | Onsite | India Apps | Project Manager - HCL Owned - Skill A | L4 | 6.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase‑1 | ABAP | ABAP Sr Con | Offshore | India Apps | Lead Consultant - Skill A | L3 | 43.5 | 0 | 2 | 2 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 5.5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase‑1 | ABAP | ABAP Con | Offshore | India Apps | Technical Consultant - Senior - Skill A | L2 | 29 | 0 | 1.5 | 1.5 | 2.5 | 3 | 3 | 3 | 3 | 3 | 3.5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase‑2 | ABAP | SAP ABAP Lead | Onsite | India Apps | Project Manager - HCL Owned - Skill A | L4 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
| Phase‑2 | ABAP | ABAP Sr Con | Offshore | India Apps | Lead Consultant - Skill A | L3 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5
| Phase‑2 | ABAP | ABAP Con | Offshore | India Apps | Technical Consultant - Senior - Skill A | L2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1